## Sheet1
Sprint Capacity Planner
| Max Limit | Team Hours |  |  | Sprint Days
Team Members | 6 |  | Team Member | Allocation | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Sprint Length (Days) | 10 |  |  | 100% | 1.5 |  | 1.5 | 2 |  | 2 |  |  | 2 | 2
Hours per day | 2 |  |  | 100% | 1.5 | 2 | 1.5 | 2 |  | 2 |  |  | 2 | 2
Focus Factor | 50% |  |  | 100% | 1.5 |  |  | 2 |  | 2 | 2 | 2 | 2 | 2
Daily stand-ups (Hours/Sprint) | 0.25 | 15 |  | 100% | 1.5 | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2
Sprint Planning Duration (Hours/Sprint) | 1.5 | 9 |  | 100% | 1.5 |  | 1.5 | 2 |  | 2 | 2 | 2 | 2
Sprint Review (Hours/Sprint) | 0.33333 | 2 |  | 100% | 1.5 | 1 | 1.5 | 2 |  | 2 | 2 |  | 2 | 2
Sprint Retrospective (Hours/Sprint) | 0.5 | 3
Sprint Refinements (Hours/Sprint) | 1.5 | 9
Other meetings (Hours/Sprint) | 0.5 | 3
Total Capacity (Hours) | 80
Total Meeting Time (Hours) | 41 |  | Total Team Time (Hours) |  | Sprint Days 10: 80
Focus Time (Hours) | 19.5
Plan Capacity (Hours) | 19.5
Plan Capacity (Days) | 2.4375
Note on D19: the sum of sprint tasks estimation should not exceed this number -Oana Adriana Soica

## Sheet2
Sprint Capacity Planner
| Max Limit | Team Hours |  |  | Sprint Days
Team Members | 5 |  | Member | Allocation | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Sprint Length (Days) | 10 |  | Person 1 | 100% | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Hours per day | 8 |  | Person 2 | 100% | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Focus Factor | 80% |  | Person 3 | 100% | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Daily stand-ups (Hours/Sprint) | 0.25 | 12.5 | Person 4 | 75% | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Planning, Review, Retrospective, Refinement (Hours/Sprint) | 4.5 | 22.5 | Person 5 | 50% | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Other meetings (Hours/Sprint) | 2 | 10 | Person 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capacity (Hours) | 334
Total Meeting Time (Hours) | 45 |  | Total Team Time (Hours) |  | Sprint Days 10: 334
Focus Time (Hours) | 57.8
Plan Capacity (Hours / Days) | 231 | 28.9

## Sheet3
| Oct |  |  |  | Noi |  |  |  | Dec |  |  |  | Jan
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3
[8 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Setup team and project
Discovery
pregatire Sprint 1
Delivery 1 - 29.11
Login organizator evenimente
[8 empty] | 1 | Sign-up | 4
[8 empty] | 2 | Sign-in | 3
[8 empty] | 3 | Reset pass | 2
Adaugare si gestionare evenimente pentru organizator
[8 empty] | 4 | US 1: adauga eveniment |  |  | 5
[8 empty] | 5 | US 2: adauga bilete per eveniment |  |  | 5
[8 empty] | 6 | US 3: modifica eveniment |  |  | 3
[8 empty] | 7 | US 4: Anuleaza eveniment |  |  | 4
....
Login user
[8 empty] | 8 | Sign-up |  |  | 4
[8 empty] | 9 | Sign-in |  |  | 3
[8 empty] | 10 | Reset pass |  |  | 1
Rezervare bilete
Achizitionare bilete
Login admin app ???/
Delivery 2 - project final demo
Note on I7: MILESTONE -Oana Adriana Soica

## Sheet4
|  | TO DO | In progress | QUA | DONE
| 1 |  |  |  | Sign-up
| 2 |  |  |  | Sign-in
| 3 |  |  |  | Reset pass
4
US 1: adauga eveniment
| 6 |  |  | US 3: modifica eveniment
....
| 8 |  |  |  | Sign-up
| 9 |  |  |  | Sign-in
| 10 |  |  |  | Reset pass